## Burndown Chart
Estimated time--> | 2017-05-12 | 2017-05-15 | 2017-05-17 | 2017-05-19 | 2017-05-22 | 2017-05-24 | 2017-05-26 | 2017-05-29 | 2017-05-31 | 2017-06-03 | Total hours
As administrator I want server to connect to external server | 2017-05-12: 4 | 0
As user I want to be able to connect to a server | 2017-05-12: 4 | 0
As guest I want to reqister to system | 2017-05-12: 10 | 0
As user I want to log in | [10 empty] | 0
As user I want my data stored | [10 empty] | 0
As user I want to see my profile | [10 empty] | 0
As user I want to manage my profile | [10 empty] | 0
As user/guest I want to see a list of current movies from server | [10 empty] | 0
As user I want to see information about chosen movie on the server | [10 empty] | 0
As user I want to have list of favourites | [10 empty] | 0
As user I want to add/remove movie from my list of favourites | [10 empty] | 0
As user I want to rate a movie | [10 empty] | 0
As administrator I want to see list of users | [10 empty] | 0
As administrator I want to managge users | [10 empty] | 0
As administratr I want to have user accounts secure | [10 empty] | 0
As owner I want proces report | [10 empty] | 0
As owner I want project report | [10 empty] | 0
As owner I want group policy in project report | [10 empty] | 0
As an owner I want javadoc | [10 empty] | 0
As owner I want user guide | [10 empty] | 0
As administrator I want to be able to get log file from server containing information | [10 empty] | 0
As user I want to see trailer for movies | [10 empty] | 0
Actual remaining hours | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Estimated remaining hours | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 4 | As administrator I want server to connect to external server
2 | Critical | 4 | As user I want to be able to connect to a server
3 | Critical | 10 | As guest I want to reqister to system
4 | Critical |  | As user I want to log in
5 | Critical |  | As user I want my data stored
6 | Critical |  | As user I want to see my profile
7 | Medium |  | As user I want to manage my profile
8 | Critical |  | As user/guest I want to see a list of current movies from server
9 | Critical |  | As user I want to see information about chosen movie on the server
10 | Medium |  | As user I want to have list of favourites
11 | Medium |  | As user I want to add/remove movie from my list of favourites
12 | Medium |  | As user I want to rate a movie
13 | Low |  | As administrator I want to see list of users
14 | Low |  | As administrator I want to managge users
15 | Medium |  | As administratr I want to have user accounts secure
15.1 | Critical |  | As owner I want proces report
15.2 | Critical |  | As owner I want project report
16 | Critical |  | As owner I want requirements in project report
17 | Critical |  | As owner I want group policy in project report
18 | Critical |  | As an owner I want javadoc
19 | Critical |  | As owner I want user guide
20 | Low |  | As administrator I want to be able to get log file from server containing information
21 | Low |  | As user I want to see trailer for movies

## 15-05
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Implement connection to extarnal server | Martin | 4 | Not Started
2 | 2 | Implement connecting to server | Martin | 4 | Not Started
3 | 3 | Create gui for registering new user | Marek | 1 | Not Started
3 | 4 | Create controller class for registering user | Marek | 1 | Not Started
3 | 5 | Implement model classes for user | Andreea | 1 | Not Started
3 | 6 | Implement sendng data via Json | Martin | 0.5 | Not Started
3 | 7 | Implement database to store users | Martin | 1 | Not Started
3 | 8 | Server connection to database | Martin | 1 | Not Started
3 | 9 | Implement adding new uer to database | Martin | 1 | Not Started
3 | 10 | Use case diagram for registering users | Andreea | 1 | Not Started
3 | 11 | Use case description for registering users | Marek, Stela | 1 | Not Started
3 | 12 | Activity diagram for registering users | Andreea | 1 | Not Started
3 | 13 | Test registering new users | Stela | 0.5 | Not Started